## October, 2026
S.N. | Task Name | Estimation (In Hours) | Comments/Remarks
1 | High Priority | -
- | Visual Hierarchy & Above-the-Fold | 18 to 24 | Covers the homepage hero and applying the new hero/section layout (cards, accordions, mid-page and end-of-page CTAs) to the ~21 destination pages (countries, Spain regions, French Riviera, Italy cities). Needs Design's approved mockups first. If the destination pages share one template, this reduces by about 10 hrs.
- | Destinations Menu & Information Architecture | 6 to 8 | Destinations landing page (card grid in priority order), clickable nav item, two-level dropdown incl. Italy's city pages, and CTA in the dropdown. Needs Design's mockup. /destinations/ currently returns "Access Restricted"; we will check this with hosting.
- | Inquiry Entry Points & Form Placement | 4 to 6 | Compact Contact Form 7 form on destination pages with the destination pre-filled, form/CTA at the end of blog posts and inner pages, and submission tracking per page (GA4 event). Needs Design's mockup.
- | Form Fields & Qualification Model | 4 to 6 | Rebuild of the Contact Form 7 form with the new fields (destinations, dates, travellers, planning for, interests) and concierge-style labels. Needs mockup and approved copy.
- | "What Happens Next" & Post-Submission Experience | 4 to 5 | 4-step strip by the form, branded thank-you page and auto-reply email. Response time and email copy to be approved by the client.
- | Budget Positioning | 1 to 2 | Client to approve the currency, budget bands and helper text before implementation.
- | CTA Consistency & Written-Inquiry Pathway | 4 to 6 | Global primary/secondary button styles, replacing the 17 CTA labels site-wide, "How It Works" link, and restyling the Luxury Italian Tours link on the Italy page. Needs Design's 1 hr button spec.
- | Typography & Heading Structure | 2 to 3 | One H1 per page, H2/H3 order, script face for display headings only, type scale in Elementor global fonts.
- | Design Standards & Spacing | 3 to 4 | Spacing scale set in Elementor Site Settings and applied together with the hero/layout work.
- | About / Founder Story | 4 to 6 | The current template About page can be unpublished/redirected right away (included). The new page needs Design's mockup and client-approved content.
- | Travel Designers / Team | 2 to 3 | "Meet Your Travel Designer" on the About page plus a compact version by the form. Needs real names, roles, bios and approved portraits from the client.
- | Content & Microcopy Quality | 1 to 2 | Fixing the verified typos and the Terms & Conditions / Privacy Policy links (page content to be provided if those pages don't exist). The FAQs "Access Restricted" response looks like a hosting/security geo-rule; we may need hosting access.
- | Mobile Typography & Page Length | 3 to 5
- | Sticky Header & Mobile Bottom Action | 3 to 4 | Sticky desktop header with the primary CTA, plus a mobile bottom bar (CTA + email).
- | One Section per Fold & Form Position | 1 to 2 | Moves the Contact form above the contact details on mobile. Cards/accordions for destination content are covered in Visual Hierarchy.
- | Cross Browser & Device Testing | 4 to 6 | Desktop, tablet and mobile on Chrome, Safari, Firefox and Edge, plus test form submissions.
2 | Medium Priority | -
- | Colours | 2 to 3
- | Hover & Focus States | 1 to 2
- | 404 Page | 2 to 3 | Built with Elementor Pro Theme Builder for desktop and mobile. Needs Design's 404 mockup and sketch illustration.
- | Mobile 404 Page | - | Included in 404 Page.
- | Top Utility Bar | 1 to 2
- | Trust Signals: Heritage, Memberships, Press | 1 to 2 | Client to confirm verified memberships/press before we add them.
- | Facts Row | 1 to 2 | Figures to be confirmed by the client.
- | Blog | 2 to 3 | Related-destination block and planning CTA added to the single-post template. Replacing stock imagery needs approved artwork.
- | Testimonials | 3 to 4 | Showing 2-3 at a time, moving them higher on the homepage, and showing destination-matched testimonials on destination pages.
- | Mobile Navigation | 2 to 3
- | Device Conventions | 1 to 2 | Hamburger/close icon in the brand line style to be provided by Design.
- | Touch Targets | 1 to 2
3 | Low Priority | -
- | Icons & Visual Consistency | 2 to 3 | Once Design provides the sketch-style icon set (SVG).
- | Social & Sharing Icons | 1 to 2
- | How It Works / Process Explanation | 2 to 3 | Uses the existing sketch illustrations; copy to be provided.
- | Pop-ups & Slide-ins | - | Not recommended for now (Strategy Only). If a slide-in is tested later, please share the design and trigger rules and we will estimate then.
- | Mobile Pop-ups & Slide-ins | - | Same as comment for Pop-ups & Slide-ins.
- | Video | - | Deferred in the audit. We will estimate once the video is produced.
| High Priority | 64 to 92
| Medium Priority | 17 to 28
| Low Priority | 5 to 8
| Total Estimated Hours | 86 to 128
Notes
The website is built on WordPress with Elementor Pro (Reobiz theme) and Contact Form 7, so all the recommended items can be built in the current setup.
These are dev hours only. Design's mockup hours (25 hrs in the audit) are separate, and dev starts after the mockups and client-approved content are ready.
The live site only opens from a US location, so we reviewed an archived copy (June 2025). Hours may change after reviewing the current site with access.
Items marked N/A in the audit (search, speed, multi-language, logo link) need no dev work.
This is just tentative estimate hours and it might be increased because we need to research and experiment on some tasks for possibilities.
Task link
https://login.smartsites.com/projects/8881/tasks/496441
Website UI/UX Audit
https://docs.google.com/document/d/10EAvGalHG1toXZFtU0Lo0sVQk5ohUCS6_V36lcAgYOg/edit
Site URL
https://www.luxeurope.net/