## Sample
S.N. | Task Name | Estimation | Comments
1. | Branding | -
- | Colors | 2 to 3 hrs
- | Typography | 2 to 3 hrs
2. | UI/UX Best Practices | -
- | Review Cross Browser Compatibility | 4 to 6 hrs
- | Hover Effect | 1 to 3 hrs
- | Pop-ups | 4 to 6 hrs | Please update us on the pop-up designs and their functions so that we can add them onto the website.
- | Search Bar | 3 to 4 hrs | We need sample design or inspiration website links for the top bars which include the Search Bar along with phone number as mentioned in the UI/UX audit.
- | Speed | 6 to 8 hrs | We can only optimized the website based on the possibilities of the DIVI builder.
- | Breadcrumbs | 2 to 3 hrs
- | Links & Buttons | 2 to 3 hrs
- | Phone Number | 1 to 2 hrs | Please review line D9 as well.
- | Videos | 1 to 2 hrs
- | Sliders and carousels or slider-carousel user-initiated | 3 to 4 hrs
- | Design Standards |  | Before proceeding with any changes, kindly verify the necessity of the changes. If very necessary, please notify DesignTeam to provide detailed information for each block on the website that requires modifications.
- | Consistency is Key |  | Please verify the necessity of this. If it's required and confirmed from the client, we will then proceed with the estimation.
- | Structure Text Fields to Match the Required Input | 1 to 2 hrs | It seems fine after inspecting form in the Book a Demo page but we can only verify and confirmed for all the forms in the website only after conducting a thorough inspection of all the test fields in the other forms on the website.
- | Leave plenty of white space between elements | 3 to 4 hrs
- | Animate top bars and popups |  | We could only inform about this after getting the design and instructions on these as we 've mentioned in row D9.
- | Incorporate human faces |  | To implement high-quality human face photos throughout the website, we also need the particular images. As the site built with DIVI builder, we might be unable to meet this requirement. However, we will implement as much as it is possible.
- | Use familiarity to your advantage |  | In order to implement this, please notify us regarding the "About Us" section design and its content as well as media to be used.We will only proceed with the estimation.
3. | Responsive Testing | -
- | Slurring your navigation | 1 to 2 hrs | Due to DIVI builder limitations, this might not yet be possible to implement. However, we will try our best and find the possible ways to acquire this.
- | The Appearance of Background Images and Icons | 1 to 2 hrs | Again this issues are primarily arising from DIVI restrictions on its responsiveness features. However, we will inspect thoroughly to identify and implement the necessary solutions.
- | Showing Data on Small Screens | 1 to 2 hrs | Same as comments above row D25.
- | Displaying too much content | 1 to 2 hrs | Same as comments above row D25.
- | Ignoring contextual conventions | 1 to 2 hrs | Same as comments above row D25.
- | Abusing touch targets | 1 to 2 hrs | Same as comments above row D25.
- | Sticky Header | 1 to 2 hrs | Same as comments above row D25.
- | Search Bar |  | As mentioned above in row D9, we can only add on the Mobile after Desktop.
- | Test Popups on Mobile |  | As mentioned above in row D8, we can only add on the Mobile after Desktop.
- | Mobile Optimized Typography | 4 to 6 hrs
- | Test the website visually | 4 to 6 hrs
- | Test for interactivity | 1 to 2 hrs | Same as comments above row D25.
- | Sticky Navigation | 1 to 2 hrs | This will be implemented after adding sticky header on mobile.
- | One section in One Fold | 4 to 6 hrs | Same as comments above row D25.
| Total Estimated Hours | 56 to 89 hrs
Notes
As the website is built using DIVI builder, we might be unable to implement some tasks due to its limitations.
This is just tentative estimate hours and it might be increased because we need to research and experiment on some tasks for possibilities.
Task link
https://login.smartsites.com/projects/3726/tasks/146084
Website UI/UX Audit
https://docs.google.com/document/d/19YnasveQjTT17ZPCMxIbFsOfaW-3IaNDtwIqQlKLuX0/edit#heading=h.i0bhsc8afjy9
Site URL
https://www.datagalaxy.com/

## July, 2024
S.N. | Task Name | Estimation (In Hours) | Comments/Remarks
1 | High Priority | -
- | Colors | 2 to 3
- | Typography | 2 to 3
- | Links & Buttons | 2 to 3
- | Consistency is Key | 4 to 6
- | High-Quality Images | 4 to 6
2 | Medium Priority | -
- | Mobile Optimized Typography | 4 to 6
- | Showing Data on Small Screens | 1 to 2 | This issues are primarily arising from builder restrictions on its responsiveness features. However, we will inspect thoroughly to identify and implement the necessary solutions.
- | Displaying too much content | 1 to 2 | Same as comment mentioned in D11
| Total Estimated Hours | 20 to 31
Notes
As the website is built on Squarespace as it uses its own native page builder and we might be unable to implement some tasks due to its limitations.
This is just tentative estimate hours and it might be increased because we need to research and experiment on some tasks for possibilities.
Task link
https://login.smartsites.com/projects/5731/tasks/273917
Website UI/UX Audit
https://docs.google.com/document/d/1kUAYdCr6L1D45TAN-sKx5uYA-gFFfEQ2w_K2ImkyEC4/edit#heading=h.dh8enj57zhgy
Site URL
https://www.krisjanovitz.com/